OPERATION AGENT

Work Split-Up: You & Parth

| 🎯 Target 7 Weeks to YC Application | 🔧 Stack Python + FastAPI, GPT-4, JSON |
| --- | --- |

Scope: Natural Language → Create Sales Order in ERPNext

# MVP Scope

Single command: Create Sales Order

Example: "Create SO for ABC Industries for 100 pieces of Product-001 at ₹500 each"

✅ Expected Output: "Sales Order SO-XXXXX created. Total: ₹50,000"

## Components to Build

| # | Component | Purpose |
| --- | --- | --- |
| 1 | Clarity Agent | Parse prompt → intent + entities (customer, items, qty, rate) |
| 2 | Context Retrieval | Load ERP URL, API key, Sales Order schema from erpnext_doctype_graph.json |
| 3 | Payload Generator | Map entities → ERPNext API payload (customer code, item code, etc.) |
| 4 | Validation | Check mandatory fields, customer/item exist |
| 5 | Execution Agent | POST to ERPNext /api/resource/Sales Order |
| 6 | Result Formatter | API response → human-readable message |

Skipped for MVP: Command Planning (single-step), Confirmation Gate (auto-execute), PostgreSQL (use JSON config)

# 7-Week Timeline

| Week | Focus |
| --- | --- |
| Week 1 | Project setup, config, ERPNext API test, Clarity Agent |
| Week 2 | Context Retrieval, Payload Generator |
| Week 3 | Validation, Execution Agent, Result Formatter |
| Week 4 | End-to-end wiring, orchestration, bug fixes |
| Week 5 | Simple UI (chat or form), deployment flow |
| Week 6 | Testing with real ERPNext, edge cases |
| Week 7 | YC demo prep, polish, docs |

# Work Split-Up

## YOUR Tasks

Your focus: Understanding layer, context, validation, orchestration.

| # | Task | Details | Week |
| --- | --- | --- | --- |
| 1 | Project Setup | FastAPI skeleton, .env config, project structure, ERPNext API connection test | 1 |
| 2 | Knowledge Base | intent_definitions.json (create_sales_order), erpnext_field_mappings.json, use existing erpnext_doctype_graph.json | 1 |
| 3 | Clarity Agent | Intent + entity extraction (customer, items, qty, rate), LLM integration, structured JSON output | 1–2 |
| 4 | Context Retrieval | Load config (ERP URL, API key), Sales Order schema from doctype graph, customer/item lookup via ERPNext API | 2 |
| 5 | Validation | Mandatory fields check, customer/item exist (using doctype graph + API lookup) | 3 |
| 6 | Result Formatter | Parse API response → success/error templates, natural language output | 3 |
| 7 | Orchestrator & API | FastAPI routes (POST /command), chain all agents, error handling | 4 |

## PARTH's Tasks

Parth's focus: Payload building, execution, integration, UI, deployment.

| # | Task | Details | Week |
| --- | --- | --- | --- |
| 1 | Payload Generator | Map entities → ERPNext payload (customer, items child table, transaction_date, defaults) | 2 |
| 2 | Execution Agent | HTTP client for ERPNext API, auth (API key), retry logic, response parsing | 3 |
| 3 | Integration & E2E | Wire agents, integration tests, fix handoffs | 4 |
| 4 | Simple UI | Chat or form input, display result (Next.js or minimal React) | 5 |
| 5 | Deployment Flow | Config setup (user enters ERP URL + API key), run instructions | 5 |
| 6 | Testing & Polish | Real ERPNext testing, edge cases, YC demo prep | 6–7 |

# Dependency Order

| YOU (parallel) | PARTH (parallel) |
| --- | --- |
| 1. Project Setup → |  |
| 2. Knowledge Base → | 1. Payload Generator (needs schema) |
| 3. Clarity Agent → |  |
| 4. Context Retrieval → | 2. Execution Agent |
| 5. Validation → | 3. Integration & E2E |
| 6. Result Formatter → |  |
| 7. Orchestrator ← | 4. Simple UI |
|  | 5. Deployment Flow |
|  | 6. Testing & Polish |

Critical Path You deliver Clarity output format + Context bundle by Week 2 so Parth can build Payload Generator. Parth delivers Execution Agent by Week 3 so you can test Result Formatter with real API.

# Config Files Needed

| File | Owner | Status |
| --- | --- | --- |
| intent_definitions.json | You | Create |
| erpnext_doctype_graph.json | — | Use existing |
| erpnext_field_mappings.json | You | Create |
| .env or config.json | Both | ERPNext URL, API key, company |

# Handoff Points

| Week | You → Parth | Parth → You |
| --- | --- | --- |
| 1 | Project structure, intent_definitions.json, Clarity output schema | — |
| 2 | Context bundle structure, validation result format | Payload format, API contract |
| 3 | Orchestrator API (request/response) | Execution result format |
| 4 | — | Integration issues, bug list |
| 5 | — | UI for testing |
| 6–7 | Edge cases, demo flow | Final polish |

# Shared Responsibilities

API contract: Agree on JSON schemas (Clarity output, Context bundle, Payload, Execution result)

Test ERPNext: Shared instance with sample Customer + Item

Slack + Linear: Daily progress in Linear, async comms in Slack

# Success Criteria

User types: "Create a sales order for ABC Industries for 100 pieces of Product-001 at ₹500 each" System creates Sales Order in ERPNext. User sees: "✅ Sales Order SO-XXXXX created. Total: ₹50,000. Customer: ABC Industries." Deployable: Manual install on customer laptop, connects to their ERPNext

# Notes

Use stubs for agents you don't own (e.g., stub Execution Agent while building Result Formatter)

Weekly sync: 30 min to align on schemas and blockers

Post-YC: Add Get SO, Search Customer, more commands